PROJECT PROPOSAL FOR

FREMONT COUNTY

May 8, 2012

Major Objectives

The Eastern Idaho Entrepreneurial Center (E Center) will conduct an Analysis of Impediments (AI) to Fair Housing Choice for the region covering Fremont, Madison, and Teton Counties in Idaho and Teton County in Wyoming, and their constituent cities of Island Park, Ashton, St. Anthony, Rexburg, Driggs, and Victor. The Summer 2012 research team will begin by conducting the Background Analysis which provides the framework for the Regional AI. Upon completion of the background analysis, the research team will begin conducting the Analysis of Segregation and Integration. As the project is anticipated to extend beyond July 2012, subsequent research teams will conduct the remaining analyses as outlined to complete the AI.

Scope of Work and Deliverables

The research team will prepare an Analysis of Impediments to Fair Housing Choice that is specific to the region covering Fremont, Madison, and Teton counties in the State of Idaho and Teton County in the State of Wyoming, and their constituent cities of Island Park, Ashton, St. Anthony, Rexburg, Driggs, and Victor through performing the following activities:

- Background analysis of the region, counties, and cities that will serve as the framework for the Regional Analysis of Impediments to include:

  - Regional and city snapshot of current demographics with a focus on protected classes and trends to include income and employment data and a housing profile.

  - Analysis of anticipated major changes (examples include: recent, on-going, or promised major public investments, such as new transit lines, commercial investments, and job opportunities, etc., and recently passed laws, reforms, or major policy changes, the impacts of which have not yet been felt).

  - Analysis of Fair Housing Successes to include highlights of major successes to Affirmatively Further Fair Housing (AFFH) and other Civil Rights successes over the last 5 years.

  - Analysis of Fair Housing Problems to include highlight of any significant civil rights/fair housing related occurrences and acknowledgment of any fair housing findings and/or lawsuits by HUD or courts or other entities, including HUD sanctions or penalties (i.e., Jim Crow, De Jure segregation, and NIMBYism).

- Analysis of Segregation and Integration to include:

  - Identification and assessment of Racial/Ethnic segregation and integration, segregation based familial status, and segregation based on disability;

  - Analysis of siting of public, assisted, and tax credit housing (where it has been located and where it will be located);

  - Analysis of land and development costs, including infrastructure costs for roads, sewers, and power; and

  - Analysis of zoning and land use barriers

- Analysis of Racially and Ethnically Concentrated Areas of Poverty (RCAPS and ECAPS) to include:

  - Location of public and assisted housing in RCAPS and ECAPS;

  - Population trends in RCAPS and ECAPS since 1940, 1990, 2000, and 2010;

  - Analysis of factors contributing to creation of RCAPS and ECAPS;

  - Gap Analysis in infrastructure, housing, and services to include: housing quality, deconcentration opportunities, job access, access to transportation, bank/loan presence or absence, availability of infrastructure (street lights, sidewalks, paved streets, public water, etc.), commercial/retail access, social services, crime rate, health care access, school quality, recreation, and libraries.

- Analysis of Disparities in Access to Opportunity to include:

  - Identification of areas of opportunity and elements of opportunity both present and missing;

  - Identification of special features of areas of opportunity;

  - Identification of areas where affordable housing are lacking, the types of affordable housing most suited for each area of opportunity, and elements of opportunity needed to make housing more affordable in the area; and

  - Identification of barriers to each area of opportunity and recommended actions to overcome the barriers.

- Analysis of Fair Housing Infrastructure to include:

  - Identification of systemic fair housing issues ; and

  - Fair housing capacity and infrastructure (what fair housing programs are available or lacking)

- Analysis of Fair Housing Physical Infrastructure (ex: major public investments slated for the region and their likely impact).

The design for this Analysis of Impediments to Fair Housing Choice follows recommendations and guidelines from the U.S. Housing and Urban Development (HUD) center, the agency that oversees all funding awarded to grantees of Sustainable Community Development Grants, as are the counties identified herein.

Project Timeline

- May 9—First client consultation—Presentation of project proposal

- May 11-25—Data collection & analysis

- May 25-29—Prepare rough draft of Background Analysis

- June 4-8—Second client consultation—presentation of rough draft

- June 11-29—Additional research as needed, refine draft

- July 7-13—Third client consultation—presentation of final deliverable

Contact Information

Intern: Barbara A Trolson, MTD	Supervisor: Laura Hernandez		      Client: Stephen Loosli

Phone: 208-227-6012			Phone: 208-356-5009, ext. 403		      Phone: 208-624-4643

Email: trolbarb@isu.edu		Email: l.hernandez@idahoecenter.org	      Email: loosli@co.fremont.id.us